## Instructions
Subcontractor Management — Required Input Data
This workbook lists EXACTLY the data the company provides. Each
sheet = one table. The system DERIVES everything else (scores,
risk, forecasts) from these records — do not fill derived fields.
✅ YOU PROVIDE (one sheet each):
• Projects | the jobs (name, client, baseline start/finish dates)
• Subcontractors | companies you work with (trade, max concurrent capacity)
• Subcontracts | the PLAN: a company's contract on a project + dates + retainage
• Schedule_of_Values | cost-code line items of each subcontract (scheduled value)
• Progress_Claims | monthly % complete per subcontract (the actuals)
• Inspections_Safety | raw QA/safety records → derive Quality & Safety scores
• Change_Orders | scope/value changes to a subcontract
⚙️ SYSTEM DERIVES (never entered — computed from the above):
• Contract value = sum of Schedule-of-Values lines (+ approved change orders)
• Planned % = from baseline schedule (start→finish) at today
• Actual % = SOV-weighted % from progress claims
• SPI / earned value / billing / retainage
• Quality & Safety scores = from Inspections_Safety records
• AI Score, Delay risk, Breach risk, Recommendation (trained models)
• Company ranking, concentration (HHI), capacity/overload

## Projects
Projects
The jobs. (shared with the Materials workbook)
project_id | name | client | start_date | planned_end_date | status
P1 | Tower A | Nasr Development | 2025-12-01 | 2027-02-03 | Active
P2 | Bridge | Ministry of Roads | 2025-11-12 | 2027-10-17 | Active
P3 | Mall | Cairo Retail Group | 2026-02-09 | 2026-12-25 | Active
P4 | Hospital | Health Authority | 2025-07-26 | 2027-08-19 | Active
P5 | Airport | Civil Aviation | 2026-01-28 | 2027-05-24 | Active
P6 | Office Park | Delta Estates | 2025-09-25 | 2026-12-17 | Active
P7 | Residential Compound | Green Homes | 2025-07-04 | 2027-08-04 | Active
P8 | Factory | Industrial Co | 2025-12-29 | 2026-12-07 | Active
P9 | University | Education Trust | 2026-01-30 | 2027-06-28 | Planned

## Subcontractors
Subcontractors
The subcontractor COMPANIES (not per-project).
vendor_id | company_name | trade | capacity_projects
V001 | ABC Electrical | Electrical | 5
V002 | XYZ Concrete | Concrete | 2
V003 | Delta HVAC | HVAC | 3
V004 | Future Plumbing | Plumbing | 2
V005 | IronCore Steel | Steel | 5
V006 | PrimePaint | Painting | 2
V007 | FineFinish | Finishing | 2
V008 | SafeGuard Fire | Fire Fighting | 3
V009 | FloorMasters | Flooring | 2
V010 | SolidMasonry | Masonry | 5
V011 | MechPro | Mechanical | 2
V012 | Volt Electric | Electrical | 3
V013 | RockSolid Concrete | Concrete | 2
V014 | CoolAir HVAC | HVAC | 3
V015 | AquaFlow Plumbing | Plumbing | 4
V016 | SteelLine | Steel | 5
V017 | ColorWorks | Painting | 3
V018 | Elite Finishing | Finishing | 2
V019 | GuardTech Fire | Fire Fighting | 4
V020 | PrimeFloor | Flooring | 3
V021 | BuildRight Masonry | Masonry | 2
V022 | PowerMech | Mechanical | 3

## Subcontracts
Subcontracts
The PLAN + current performance. Quality/Safety: provide here OR via Inspections_Safety.
subcontract_id | vendor_id | project_id | title | start_date | planned_end_date | status | retainage_pct | quality_score | safety_score | inspection_pass | delay_days | open_issues
S001 | V001 | P3 | Electrical — Mall | 2026-02-04 | 2026-08-13 | Active | 10 | 83.2 | 90.9 | 92 | 4 | 3
S002 | V001 | P4 | Electrical — Hospital | 2026-02-13 | 2027-03-27 | Active | 5 | 80.1 | 84.6 | 92.7 | 7 | 4
S003 | V002 | P5 | Concrete — Airport | 2026-02-20 | 2027-02-09 | Active | 5 | 83.3 | 85.6 | 91.5 | 4 | 4
S004 | V002 | P6 | Concrete — Office Park | 2026-01-11 | 2026-12-15 | Active | 5 | 92.4 | 86.6 | 86 | 3 | 3
S005 | V002 | P4 | Concrete — Hospital | 2026-04-26 | 2026-10-23 | Active | 10 | 92.5 | 86.9 | 90.5 | 3 | 1
S006 | V003 | P6 | HVAC — Office Park | 2026-03-16 | 2027-01-12 | Active | 5 | 77.5 | 74.5 | 81.9 | 9 | 4
S007 | V004 | P6 | Plumbing — Office Park | 2026-03-26 | 2027-02-25 | Active | 5 | 78.9 | 77.4 | 79.8 | 8 | 5
S008 | V004 | P8 | Plumbing — Factory | 2026-02-23 | 2026-12-14 | Active | 10 | 80.8 | 75.6 | 85.2 | 12 | 6
S009 | V005 | P7 | Steel — Residential Compound | 2026-04-01 | 2027-01-28 | Active | 10 | 82.3 | 75.7 | 89.6 | 6 | 5
S010 | V006 | P6 | Painting — Office Park | 2026-01-02 | 2026-11-18 | Active | 10 | 87.4 | 93.7 | 90.6 | 2 | 2
S011 | V006 | P2 | Painting — Bridge | 2026-04-19 | 2026-10-31 | Active | 5 | 93.4 | 93.9 | 94 | 2 | 3
S012 | V007 | P3 | Finishing — Mall | 2026-01-21 | 2026-12-25 | Active | 10 | 83.1 | 88.7 | 93.9 | 4 | 3
S013 | V008 | P4 | Fire Fighting — Hospital | 2026-03-13 | 2027-01-02 | Active | 5 | 78.3 | 81.3 | 85.1 | 10 | 4
S014 | V008 | P6 | Fire Fighting — Office Park | 2026-02-02 | 2026-08-19 | Active | 5 | 83.6 | 77.1 | 91.9 | 10 | 3
S015 | V009 | P4 | Flooring — Hospital | 2026-02-01 | 2026-12-09 | Active | 5 | 79.2 | 94 | 88 | 5 | 4
S016 | V009 | P2 | Flooring — Bridge | 2026-05-01 | 2027-01-03 | Active | 10 | 88.6 | 82.4 | 86 | 3 | 3
S017 | V010 | P2 | Masonry — Bridge | 2026-03-15 | 2027-05-09 | Active | 10 | 84.6 | 79.1 | 91.8 | 7 | 4
S018 | V011 | P5 | Mechanical — Airport | 2026-04-01 | 2027-05-24 | Active | 5 | 79.6 | 79 | 86.4 | 5 | 4
S019 | V011 | P1 | Mechanical — Tower A | 2026-02-01 | 2027-01-15 | Active | 5 | 84.7 | 75.7 | 88.6 | 11 | 5
S020 | V011 | P2 | Mechanical — Bridge | 2026-02-01 | 2026-09-10 | Active | 10 | 86.9 | 83.2 | 84 | 6 | 5
S021 | V012 | P6 | Electrical — Office Park | 2026-04-06 | 2026-10-03 | Active | 10 | 91.9 | 86.4 | 99.9 | 0 | 3
S022 | V013 | P7 | Concrete — Residential Compound | 2026-02-28 | 2027-02-27 | Active | 5 | 93 | 91.5 | 97.7 | 1 | 2
S023 | V014 | P4 | HVAC — Hospital | 2026-05-15 | 2026-11-21 | Active | 10 | 82.9 | 84.9 | 86.3 | 7 | 4
S024 | V014 | P1 | HVAC — Tower A | 2026-01-08 | 2026-07-23 | Active | 5 | 77.8 | 84 | 89.4 | 10 | 4
S025 | V015 | P2 | Plumbing — Bridge | 2026-04-15 | 2027-01-04 | Active | 10 | 84.6 | 87.4 | 86.5 | 6 | 4
S026 | V015 | P5 | Plumbing — Airport | 2026-04-01 | 2026-12-16 | Active | 5 | 78.4 | 82.2 | 94.1 | 7 | 2
S027 | V016 | P5 | Steel — Airport | 2026-04-24 | 2027-04-19 | Active | 10 | 76.2 | 90.5 | 94.5 | 3 | 2
S028 | V017 | P1 | Painting — Tower A | 2026-03-19 | 2026-12-19 | Active | 5 | 87.5 | 90.5 | 95.7 | 0 | 0
S029 | V017 | P6 | Painting — Office Park | 2026-02-16 | 2027-03-03 | Active | 5 | 93.9 | 90.8 | 90.2 | 1 | 2
S030 | V017 | P3 | Painting — Mall | 2026-04-20 | 2026-11-29 | Active | 5 | 86.2 | 89.1 | 92.1 | 3 | 2
S031 | V018 | P4 | Finishing — Hospital | 2026-02-26 | 2027-03-07 | Active | 5 | 92.5 | 89.7 | 92.4 | 1 | 2
S032 | V018 | P8 | Finishing — Factory | 2026-02-15 | 2026-10-22 | Active | 10 | 87.4 | 88.3 | 97.2 | 3 | 3
S033 | V019 | P7 | Fire Fighting — Residential Compound | 2026-01-21 | 2026-12-17 | Active | 10 | 72.5 | 86.2 | 80.9 | 11 | 3
S034 | V020 | P1 | Flooring — Tower A | 2026-03-06 | 2026-10-04 | Active | 10 | 100 | 92.8 | 94.9 | 0 | 2
S035 | V020 | P6 | Flooring — Office Park | 2026-03-21 | 2027-01-16 | Active | 10 | 89.4 | 94.8 | 95.6 | 0 | 1
S036 | V021 | P7 | Masonry — Residential Compound | 2026-02-10 | 2026-09-28 | Active | 10 | 69.2 | 80.7 | 85.7 | 11 | 6
S037 | V021 | P3 | Masonry — Mall | 2026-01-18 | 2026-10-31 | Active | 10 | 81.9 | 84.3 | 87.1 | 8 | 6
S038 | V022 | P6 | Mechanical — Office Park | 2026-01-08 | 2027-01-14 | Active | 5 | 79.9 | 88.6 | 86.5 | 7 | 4
S039 | V022 | P2 | Mechanical — Bridge | 2026-04-30 | 2026-11-08 | Active | 5 | 86.7 | 78.7 | 85.1 | 4 | 2
S040 | V022 | P7 | Mechanical — Residential Compound | 2025-12-18 | 2026-09-10 | Active | 5 | 74.3 | 81.1 | 88.5 | 9 | 4

## Schedule_of_Values
Schedule_of_Values
Cost-code breakdown of each subcontract. Sum of scheduled_value = contract. percent_complete = current % of the line.
line_id | subcontract_id | cost_code | description | scheduled_value | percent_complete
S001-L1 | S001 | 16-10 | Wiring & conduit | 64178 | 70.7
S001-L2 | S001 | 16-50 | Lighting | 64946 | 71.3
S001-L3 | S001 | 16-70 | Low voltage | 76138 | 75.5
S001-L4 | S001 | 01-50 | General conditions | 99072 | 85.8
S002-L1 | S002 | 16-10 | Wiring & conduit | 61816 | 30.3
S002-L2 | S002 | 16-50 | Lighting | 80275 | 41.1
S002-L3 | S002 | 16-70 | Low voltage | 71805 | 32.9
S002-L4 | S002 | 01-50 | General conditions | 51898 | 45.4
S003-L1 | S003 | 03-30 | Cast-in-place concrete | 224250 | 31.1
S003-L2 | S003 | 03-20 | Reinforcement | 250528 | 50.8
S003-L3 | S003 | 03-10 | Formwork | 445634 | 35.2
S004-L1 | S004 | 03-30 | Cast-in-place concrete | 200795 | 49.9
S004-L2 | S004 | 03-20 | Reinforcement | 183640 | 50.1
S004-L3 | S004 | 03-10 | Formwork | 197205 | 43
S004-L4 | S004 | 01-50 | General conditions | 186209 | 55.7
S005-L1 | S005 | 03-30 | Cast-in-place concrete | 213201 | 46.8
S005-L2 | S005 | 03-20 | Reinforcement | 109175 | 54.5
S005-L3 | S005 | 03-10 | Formwork | 135522 | 46.1
S005-L4 | S005 | 01-50 | General conditions | 167735 | 43
S006-L1 | S006 | 15-70 | Air handling | 84796 | 41.9
S006-L2 | S006 | 15-80 | Ductwork | 174593 | 47.2
S006-L3 | S006 | 15-90 | Controls | 103618 | 43.5
S007-L1 | S007 | 15-40 | Piping | 317521 | 24.8
S007-L2 | S007 | 15-45 | Fixtures | 320501 | 31.8
S007-L3 | S007 | 15-30 | Drainage | 301426 | 27.9
S008-L1 | S008 | 15-40 | Piping | 292082 | 36.3
S008-L2 | S008 | 15-45 | Fixtures | 173570 | 36.5
S008-L3 | S008 | 15-30 | Drainage | 144628 | 46.6
S008-L4 | S008 | 01-50 | General conditions | 145910 | 53.2
S009-L1 | S009 | 05-10 | Structural steel | 77032 | 40.8
S009-L2 | S009 | 05-50 | Metal fabrications | 189860 | 25
S009-L3 | S009 | 05-30 | Decking | 160408 | 26.8
S009-L4 | S009 | 01-50 | General conditions | 126449 | 46.8
S010-L1 | S010 | 09-90 | Painting | 78633 | 62.3
S010-L2 | S010 | 09-91 | Coatings | 109811 | 61.2
S010-L3 | S010 | 01-50 | General conditions | 71527 | 46.4
S011-L1 | S011 | 09-90 | Painting | 165557 | 56.9
S011-L2 | S011 | 09-91 | Coatings | 187286 | 58.1
S011-L3 | S011 | 01-50 | General conditions | 144805 | 40.1
S012-L1 | S012 | 09-25 | Plaster | 169082 | 58.5
S012-L2 | S012 | 09-51 | Ceilings | 147401 | 38.7
S012-L3 | S012 | 09-70 | Wall finishes | 140503 | 41.9
S012-L4 | S012 | 01-50 | General conditions | 182547 | 38.3
S013-L1 | S013 | 15-30 | Sprinklers | 243296 | 31.6
S013-L2 | S013 | 13-90 | Fire pumps | 279270 | 38.8
S013-L3 | S013 | 01-50 | General conditions | 292588 | 48
S014-L1 | S014 | 15-30 | Sprinklers | 197500 | 72.7
S014-L2 | S014 | 13-90 | Fire pumps | 92520 | 60.2
S014-L3 | S014 | 01-50 | General conditions | 171925 | 78
S015-L1 | S015 | 09-65 | Resilient flooring | 123404 | 46.8
S015-L2 | S015 | 09-68 | Carpet | 184257 | 36.7
S015-L3 | S015 | 09-30 | Tiling | 78320 | 44.2
S015-L4 | S015 | 01-50 | General conditions | 158913 | 51.2
S016-L1 | S016 | 09-65 | Resilient flooring | 293324 | 36.8
S016-L2 | S016 | 09-68 | Carpet | 239684 | 34.6
S016-L3 | S016 | 09-30 | Tiling | 351121 | 21.1
S017-L1 | S017 | 04-20 | Unit masonry | 72658 | 29.6
S017-L2 | S017 | 04-40 | Stone | 168810 | 19.8
S017-L3 | S017 | 01-50 | General conditions | 70528 | 17
S018-L1 | S018 | 15-10 | Mechanical piping | 148362 | 16.5
S018-L2 | S018 | 15-20 | Pumps | 187826 | 8.6
S018-L3 | S018 | 15-60 | Equipment | 127316 | 14.2
S019-L1 | S019 | 15-10 | Mechanical piping | 329474 | 33.9
S019-L2 | S019 | 15-20 | Pumps | 181011 | 50.3
S019-L3 | S019 | 15-60 | Equipment | 160261 | 46.6
S019-L4 | S019 | 01-50 | General conditions | 163484 | 32.5
S020-L1 | S020 | 15-10 | Mechanical piping | 241275 | 54.6
S020-L2 | S020 | 15-20 | Pumps | 206067 | 58.6
S020-L3 | S020 | 15-60 | Equipment | 137655 | 51.3
S020-L4 | S020 | 01-50 | General conditions | 130662 | 58.3
S021-L1 | S021 | 16-10 | Wiring & conduit | 96338 | 48.2
S021-L2 | S021 | 16-50 | Lighting | 67345 | 44
S021-L3 | S021 | 16-70 | Low voltage | 96528 | 51.5
S021-L4 | S021 | 01-50 | General conditions | 48512 | 42.9
S022-L1 | S022 | 03-30 | Cast-in-place concrete | 58954 | 45.3
S022-L2 | S022 | 03-20 | Reinforcement | 144764 | 47.9
S022-L3 | S022 | 03-10 | Formwork | 150906 | 49.8
S023-L1 | S023 | 15-70 | Air handling | 185177 | 13.4
S023-L2 | S023 | 15-80 | Ductwork | 200971 | 25.7
S023-L3 | S023 | 15-90 | Controls | 116347 | 18.8
S024-L1 | S024 | 15-70 | Air handling | 234631 | 78.8
S024-L2 | S024 | 15-80 | Ductwork | 128073 | 88.9
S024-L3 | S024 | 15-90 | Controls | 218997 | 84.3
S025-L1 | S025 | 15-40 | Piping | 231967 | 41.5
S025-L2 | S025 | 15-45 | Fixtures | 131059 | 20.6
S025-L3 | S025 | 15-30 | Drainage | 203264 | 23.4
S025-L4 | S025 | 01-50 | General conditions | 203962 | 29.9
S026-L1 | S026 | 15-40 | Piping | 301296 | 56.3
S026-L2 | S026 | 15-45 | Fixtures | 219971 | 56.2
S026-L3 | S026 | 15-30 | Drainage | 384111 | 41.7
S027-L1 | S027 | 05-10 | Structural steel | 127877 | 17.9
S027-L2 | S027 | 05-50 | Metal fabrications | 94264 | 25.6
S027-L3 | S027 | 05-30 | Decking | 207383 | 18.2
S027-L4 | S027 | 01-50 | General conditions | 168998 | 17.2
S028-L1 | S028 | 09-90 | Painting | 175609 | 27.5
S028-L2 | S028 | 09-91 | Coatings | 189349 | 28.8
S028-L3 | S028 | 01-50 | General conditions | 158154 | 46.3
S029-L1 | S029 | 09-90 | Painting | 314665 | 50.1
S029-L2 | S029 | 09-91 | Coatings | 320737 | 34
S029-L3 | S029 | 01-50 | General conditions | 233585 | 50.4
S030-L1 | S030 | 09-90 | Painting | 117796 | 37.2
S030-L2 | S030 | 09-91 | Coatings | 193081 | 33.2
S030-L3 | S030 | 01-50 | General conditions | 179687 | 39.1
S031-L1 | S031 | 09-25 | Plaster | 104552 | 31.3
S031-L2 | S031 | 09-51 | Ceilings | 94802 | 32.5
S031-L3 | S031 | 09-70 | Wall finishes | 148362 | 43.1
S032-L1 | S032 | 09-25 | Plaster | 75954 | 63.6
S032-L2 | S032 | 09-51 | Ceilings | 60814 | 65
S032-L3 | S032 | 09-70 | Wall finishes | 83906 | 46.8
S032-L4 | S032 | 01-50 | General conditions | 72768 | 66.1
S033-L1 | S033 | 15-30 | Sprinklers | 156704 | 37.7
S033-L2 | S033 | 13-90 | Fire pumps | 79666 | 46.5
S033-L3 | S033 | 01-50 | General conditions | 64826 | 50.4
S034-L1 | S034 | 09-65 | Resilient flooring | 218133 | 67.3
S034-L2 | S034 | 09-68 | Carpet | 111404 | 62.7
S034-L3 | S034 | 09-30 | Tiling | 103800 | 58.7
S034-L4 | S034 | 01-50 | General conditions | 186440 | 67.8
S035-L1 | S035 | 09-65 | Resilient flooring | 266201 | 28.9
S035-L2 | S035 | 09-68 | Carpet | 219551 | 40.3
S035-L3 | S035 | 09-30 | Tiling | 147150 | 44.5
S036-L1 | S036 | 04-20 | Unit masonry | 107308 | 58.1
S036-L2 | S036 | 04-40 | Stone | 223657 | 44
S036-L3 | S036 | 01-50 | General conditions | 123513 | 43.7
S037-L1 | S037 | 04-20 | Unit masonry | 164660 | 59
S037-L2 | S037 | 04-40 | Stone | 64195 | 54.7
S037-L3 | S037 | 01-50 | General conditions | 60637 | 61.8
S038-L1 | S038 | 15-10 | Mechanical piping | 143317 | 34.9
S038-L2 | S038 | 15-20 | Pumps | 158927 | 35
S038-L3 | S038 | 15-60 | Equipment | 100862 | 43.1
S038-L4 | S038 | 01-50 | General conditions | 65172 | 54.3
S039-L1 | S039 | 15-10 | Mechanical piping | 76969 | 37.4
S039-L2 | S039 | 15-20 | Pumps | 95985 | 47
S039-L3 | S039 | 15-60 | Equipment | 155153 | 46
S039-L4 | S039 | 01-50 | General conditions | 58894 | 28.5
S040-L1 | S040 | 15-10 | Mechanical piping | 132100 | 63.2
S040-L2 | S040 | 15-20 | Pumps | 210867 | 56.7
S040-L3 | S040 | 15-60 | Equipment | 141513 | 74.7

## Progress_Claims
Progress_Claims
Monthly progress billing per subcontract → gives the actual % (S-curve).
claim_id | subcontract_id | period_end | percent_complete | completed_value
S001-C1 | S001 | 2026-03-06 | 16.2 | 49302
S001-C2 | S001 | 2026-04-05 | 32.4 | 98604
S001-C3 | S001 | 2026-05-05 | 48.6 | 147906
S001-C4 | S001 | 2026-06-04 | 64.8 | 197208
S001-C5 | S001 | 2026-07-04 | 81 | 246511
S002-C1 | S002 | 2026-03-15 | 7.1 | 18871
S002-C2 | S002 | 2026-04-14 | 14.1 | 37477
S002-C3 | S002 | 2026-05-14 | 21.2 | 56348
S002-C4 | S002 | 2026-06-13 | 28.3 | 75220
S002-C5 | S002 | 2026-07-13 | 35.4 | 94091
S003-C1 | S003 | 2026-03-22 | 8.6 | 79155
S003-C2 | S003 | 2026-04-21 | 17.1 | 157390
S003-C3 | S003 | 2026-05-21 | 25.7 | 236546
S003-C4 | S003 | 2026-06-20 | 34.3 | 315701
S003-C5 | S003 | 2026-07-20 | 42.8 | 393936
S004-C1 | S004 | 2026-02-10 | 8.7 | 66803
S004-C2 | S004 | 2026-03-12 | 17.5 | 134374
S004-C3 | S004 | 2026-04-11 | 26.2 | 201176
S004-C4 | S004 | 2026-05-11 | 35 | 268747
S004-C5 | S004 | 2026-06-10 | 43.7 | 335550
S004-C6 | S004 | 2026-07-10 | 52.5 | 403121
S005-C1 | S005 | 2026-05-26 | 21.8 | 136388
S005-C2 | S005 | 2026-06-25 | 43.6 | 272776
S006-C1 | S006 | 2026-04-15 | 9.3 | 33760
S006-C2 | S006 | 2026-05-15 | 18.7 | 67882
S006-C3 | S006 | 2026-06-14 | 28 | 101642
S006-C4 | S006 | 2026-07-14 | 37.3 | 135402
S007-C1 | S007 | 2026-04-25 | 10.4 | 97703
S007-C2 | S007 | 2026-05-25 | 20.9 | 196345
S007-C3 | S007 | 2026-06-24 | 31.3 | 294047
S008-C1 | S008 | 2026-03-25 | 10.9 | 82425
S008-C2 | S008 | 2026-04-24 | 21.8 | 164849
S008-C3 | S008 | 2026-05-24 | 32.7 | 247274
S008-C4 | S008 | 2026-06-23 | 43.6 | 329699
S009-C1 | S009 | 2026-05-01 | 11.6 | 64235
S009-C2 | S009 | 2026-05-31 | 23.3 | 129023
S009-C3 | S009 | 2026-06-30 | 34.9 | 193258
S010-C1 | S010 | 2026-02-01 | 8.9 | 23137
S010-C2 | S010 | 2026-03-03 | 17.8 | 46275
S010-C3 | S010 | 2026-04-02 | 26.7 | 69412
S010-C4 | S010 | 2026-05-02 | 35.6 | 92549
S010-C5 | S010 | 2026-06-01 | 44.4 | 115427
S010-C6 | S010 | 2026-07-01 | 53.3 | 138564
S011-C1 | S011 | 2026-05-19 | 16.3 | 81117
S011-C2 | S011 | 2026-06-18 | 32.7 | 162731
S011-C3 | S011 | 2026-07-18 | 49 | 243848
S012-C1 | S012 | 2026-02-20 | 8.2 | 52442
S012-C2 | S012 | 2026-03-22 | 16.4 | 104883
S012-C3 | S012 | 2026-04-21 | 24.7 | 157965
S012-C4 | S012 | 2026-05-21 | 32.9 | 210406
S012-C5 | S012 | 2026-06-20 | 41.1 | 262848
S012-C6 | S012 | 2026-07-20 | 49.3 | 315290
S013-C1 | S013 | 2026-04-12 | 9.4 | 76624
S013-C2 | S013 | 2026-05-12 | 18.7 | 152434
S013-C3 | S013 | 2026-06-11 | 28.1 | 229058
S013-C4 | S013 | 2026-07-11 | 37.4 | 304867
S014-C1 | S014 | 2026-03-04 | 13.8 | 63749
S014-C2 | S014 | 2026-04-03 | 27.5 | 127035
S014-C3 | S014 | 2026-05-03 | 41.3 | 190784
S014-C4 | S014 | 2026-06-02 | 55.1 | 254532
S014-C5 | S014 | 2026-07-02 | 68.8 | 317819
S015-C1 | S015 | 2026-03-03 | 9.7 | 52855
S015-C2 | S015 | 2026-04-02 | 19.3 | 105165
S015-C3 | S015 | 2026-05-02 | 29 | 158019
S015-C4 | S015 | 2026-06-01 | 38.6 | 210329
S015-C5 | S015 | 2026-07-01 | 48.3 | 263184
S016-C1 | S016 | 2026-05-31 | 13.5 | 119357
S016-C2 | S016 | 2026-06-30 | 26.9 | 237831
S017-C1 | S017 | 2026-04-14 | 5.2 | 16224
S017-C2 | S017 | 2026-05-14 | 10.5 | 32760
S017-C3 | S017 | 2026-06-13 | 15.7 | 48983
S017-C4 | S017 | 2026-07-13 | 20.9 | 65207
S018-C1 | S018 | 2026-05-01 | 6.7 | 31055
S018-C2 | S018 | 2026-05-31 | 13.4 | 62110
S018-C3 | S018 | 2026-06-30 | 20.1 | 93164
S019-C1 | S019 | 2026-03-03 | 8.2 | 68407
S019-C2 | S019 | 2026-04-02 | 16.5 | 137648
S019-C3 | S019 | 2026-05-02 | 24.7 | 206055
S019-C4 | S019 | 2026-06-01 | 32.9 | 274462
S019-C5 | S019 | 2026-07-01 | 41.1 | 342869
S020-C1 | S020 | 2026-03-03 | 11.9 | 85163
S020-C2 | S020 | 2026-04-02 | 23.8 | 170327
S020-C3 | S020 | 2026-05-02 | 35.7 | 255490
S020-C4 | S020 | 2026-06-01 | 47.6 | 340654
S020-C5 | S020 | 2026-07-01 | 59.6 | 426533
S021-C1 | S021 | 2026-05-06 | 18 | 55570
S021-C2 | S021 | 2026-06-05 | 35.9 | 110832
S021-C3 | S021 | 2026-07-05 | 53.9 | 166402
S022-C1 | S022 | 2026-03-30 | 10.6 | 37590
S022-C2 | S022 | 2026-04-29 | 21.1 | 74826
S022-C3 | S022 | 2026-05-29 | 31.7 | 112416
S022-C4 | S022 | 2026-06-28 | 42.3 | 150006
S023-C1 | S023 | 2026-06-14 | 12.5 | 62812
S023-C2 | S023 | 2026-07-14 | 24.9 | 125121
S024-C1 | S024 | 2026-02-07 | 14.2 | 82602
S024-C2 | S024 | 2026-03-09 | 28.4 | 165203
S024-C3 | S024 | 2026-04-08 | 42.6 | 247805
S024-C4 | S024 | 2026-05-08 | 56.8 | 330406
S024-C5 | S024 | 2026-06-07 | 71.1 | 413589
S024-C6 | S024 | 2026-07-07 | 85.3 | 496191
S025-C1 | S025 | 2026-05-15 | 10.1 | 77795
S025-C2 | S025 | 2026-06-14 | 20.1 | 154821
S025-C3 | S025 | 2026-07-14 | 30.2 | 232616
S026-C1 | S026 | 2026-05-01 | 14.8 | 133996
S026-C2 | S026 | 2026-05-31 | 29.6 | 267992
S026-C3 | S026 | 2026-06-30 | 44.4 | 401988
S027-C1 | S027 | 2026-05-24 | 10.1 | 60451
S027-C2 | S027 | 2026-06-23 | 20.2 | 120901
S028-C1 | S028 | 2026-04-18 | 9.6 | 50219
S028-C2 | S028 | 2026-05-18 | 19.2 | 100438
S028-C3 | S028 | 2026-06-17 | 28.7 | 150133
S028-C4 | S028 | 2026-07-17 | 38.3 | 200352
S029-C1 | S029 | 2026-03-18 | 9 | 78209
S029-C2 | S029 | 2026-04-17 | 17.9 | 155549
S029-C3 | S029 | 2026-05-17 | 26.9 | 233758
S029-C4 | S029 | 2026-06-16 | 35.9 | 311966
S029-C5 | S029 | 2026-07-16 | 44.9 | 390175
S030-C1 | S030 | 2026-05-20 | 13.2 | 64754
S030-C2 | S030 | 2026-06-19 | 26.3 | 129018
S030-C3 | S030 | 2026-07-19 | 39.5 | 193773
S031-C1 | S031 | 2026-03-28 | 8.9 | 30947
S031-C2 | S031 | 2026-04-27 | 17.8 | 61894
S031-C3 | S031 | 2026-05-27 | 26.7 | 92840
S031-C4 | S031 | 2026-06-26 | 35.6 | 123787
S032-C1 | S032 | 2026-03-17 | 11.3 | 33159
S032-C2 | S032 | 2026-04-16 | 22.6 | 66318
S032-C3 | S032 | 2026-05-16 | 34 | 99770
S032-C4 | S032 | 2026-06-15 | 45.3 | 132929
S032-C5 | S032 | 2026-07-15 | 56.6 | 166088
S033-C1 | S033 | 2026-02-20 | 7.7 | 23192
S033-C2 | S033 | 2026-03-22 | 15.3 | 46083
S033-C3 | S033 | 2026-04-21 | 23 | 69275
S033-C4 | S033 | 2026-05-21 | 30.7 | 92467
S033-C5 | S033 | 2026-06-20 | 38.3 | 115358
S033-C6 | S033 | 2026-07-20 | 46 | 138551
S034-C1 | S034 | 2026-04-05 | 16.3 | 101024
S034-C2 | S034 | 2026-05-05 | 32.7 | 202667
S034-C3 | S034 | 2026-06-04 | 49 | 303691
S034-C4 | S034 | 2026-07-04 | 65.4 | 405334
S035-C1 | S035 | 2026-04-20 | 10.1 | 63923
S035-C2 | S035 | 2026-05-20 | 20.2 | 127846
S035-C3 | S035 | 2026-06-19 | 30.3 | 191769
S035-C4 | S035 | 2026-07-19 | 40.4 | 255692
S036-C1 | S036 | 2026-03-12 | 10.1 | 45902
S036-C2 | S036 | 2026-04-11 | 20.2 | 91805
S036-C3 | S036 | 2026-05-11 | 30.3 | 137707
S036-C4 | S036 | 2026-06-10 | 40.3 | 183155
S036-C5 | S036 | 2026-07-10 | 50.4 | 229057
S037-C1 | S037 | 2026-02-17 | 9.5 | 27502
S037-C2 | S037 | 2026-03-19 | 18.9 | 54714
S037-C3 | S037 | 2026-04-18 | 28.4 | 82216
S037-C4 | S037 | 2026-05-18 | 37.8 | 109428
S037-C5 | S037 | 2026-06-17 | 47.3 | 136930
S037-C6 | S037 | 2026-07-17 | 56.7 | 164142
S038-C1 | S038 | 2026-02-07 | 7.5 | 35121
S038-C2 | S038 | 2026-03-09 | 15 | 70242
S038-C3 | S038 | 2026-04-08 | 22.5 | 105363
S038-C4 | S038 | 2026-05-08 | 30 | 140484
S038-C5 | S038 | 2026-06-07 | 37.5 | 175605
S038-C6 | S038 | 2026-07-07 | 45 | 210726
S039-C1 | S039 | 2026-05-30 | 19.8 | 76626
S039-C2 | S039 | 2026-06-29 | 39.6 | 153252
S040-C1 | S040 | 2026-01-17 | 9.8 | 47479
S040-C2 | S040 | 2026-02-16 | 19.6 | 94958
S040-C3 | S040 | 2026-03-18 | 29.4 | 142437
S040-C4 | S040 | 2026-04-17 | 39.2 | 189916
S040-C5 | S040 | 2026-05-17 | 49 | 237395
S040-C6 | S040 | 2026-06-16 | 58.8 | 284874
S040-C7 | S040 | 2026-07-16 | 68.6 | 332353

## Inspections_Safety
Inspections_Safety
Raw QA & safety records per subcontract. System derives Quality & Safety scores. (example rows)
subcontract_id | period_end | inspections_total | inspections_passed | ncrs_raised | ncrs_closed | recordable_incidents | man_hours
S001 | 2026-06-30 | 23 | 22 | 3 | 3 | 1 | 180000
S002 | 2026-06-30 | 18 | 15 | 5 | 4 | 0 | 120000

## Change_Orders
Change_Orders
Scope/value changes. Approved orders add a line to the contract. (example rows)
co_id | subcontract_id | description | amount | status | co_date
S001-CO1 | S001 | Added extra floor | 80000 | Approved | 2026-05-10
S002-CO1 | S002 | Reduced scope | -25000 | Pending | 2026-06-01