## Instructions
Material Procurement — Required Input Data
This workbook lists EXACTLY the data the company provides. Each
sheet = one table. The system DERIVES everything else (scores,
risk, forecasts) from these records — do not fill derived fields.
✅ YOU PROVIDE (one sheet each):
• Projects | the jobs (shared with the Subcontractor workbook)
• Suppliers | your material suppliers (category)
• Materials_Catalog | item master (name, category, unit)
• Requirements_BOQ | per project: required qty, reorder point, consumed to date
• Purchase_Orders | commitments to a supplier for a project
• PO_Lines | the materials & quantities & unit prices on each PO
• Deliveries_GRN | goods receipts (qty received, rejected, dates)
• Invoices | supplier invoices → 3-way match against PO & delivery
⚙️ SYSTEM DERIVES (never entered — computed from the above):
• Current stock = delivered (accepted) − consumed
• On-order qty = ordered − received on open POs
• Lead time = avg(received − ordered) per supplier
• On-time % = on-time deliveries ÷ total deliveries
• Defect rate = rejected ÷ received per supplier
• 3-way match = PO vs delivery vs invoice (Matched / Exception)
• Demand forecast, reorder qty, delivery-delay risk, supplier score (models)

## Projects
Projects
The jobs. (shared with the Subcontractor workbook)
project_id | name | client | start_date | planned_end_date | status
P1 | Tower A | Nasr Development | 2025-12-01 | 2027-02-03 | Active
P2 | Bridge | Ministry of Roads | 2025-11-12 | 2027-10-17 | Active
P3 | Mall | Cairo Retail Group | 2026-02-09 | 2026-12-25 | Active
P4 | Hospital | Health Authority | 2025-07-26 | 2027-08-19 | Active
P5 | Airport | Civil Aviation | 2026-01-28 | 2027-05-24 | Active
P6 | Office Park | Delta Estates | 2025-09-25 | 2026-12-17 | Active
P7 | Residential Compound | Green Homes | 2025-07-04 | 2027-08-04 | Active
P8 | Factory | Industrial Co | 2025-12-29 | 2026-12-07 | Active
P9 | University | Education Trust | 2026-01-30 | 2027-06-28 | Planned

## Suppliers
Suppliers
Your material suppliers.
supplier_id | name | category
SUP-A | Nile Building Supplies | General
SUP-B | Delta Steel Co | Steel
SUP-C | Cairo Cement | Concrete
SUP-D | ProPaint Trading | Finishing
SUP-E | PipeMax | Plumbing
SUP-F | ElectroSupply | Electrical
SUP-G | AggregateOne | Aggregate
SUP-H | GlassWorks | Glazing

## Materials_Catalog
Materials_Catalog
Item master (the materials you buy).
material_id | name | category | unit
M01 | Cement | Concrete | bag
M02 | Steel Rebar | Steel | ton
M03 | Bricks | Masonry | 1000 pcs
M04 | Paint | Finishing | liter
M05 | Sand | Aggregate | m3
M06 | Gravel | Aggregate | m3
M07 | Timber | Wood | m3
M08 | Glass Panels | Glazing | m2
M09 | Ceramic Tiles | Finishing | m2
M10 | PVC Pipes | Plumbing | m
M11 | Electrical Cable | Electrical | m
M12 | Insulation | Finishing | m2
M13 | Concrete Blocks | Masonry | 1000 pcs
M14 | Gypsum Board | Finishing | m2

## Requirements_BOQ
Requirements_BOQ
Per-project material need (BOQ) + reorder point + qty consumed on site.
req_id | project_id | material_id | required_qty | minimum_stock | consumed_qty
R001 | P1 | M09 | 982 | 337 | 679
R002 | P1 | M13 | 1477 | 342 | 779
R003 | P1 | M12 | 3845 | 590 | 897
R004 | P1 | M11 | 8261 | 1753 | 3044
R005 | P2 | M11 | 2693 | 474 | 1524
R006 | P2 | M09 | 726 | 253 | 213
R007 | P2 | M04 | 4941 | 947 | 1172
R008 | P2 | M08 | 2061 | 568 | 810
R009 | P2 | M13 | 11571 | 3366 | 3694
R010 | P3 | M01 | 6607 | 1113 | 4536
R011 | P3 | M14 | 886 | 146 | 442
R012 | P3 | M03 | 10852 | 3155 | 6170
R013 | P3 | M05 | 1422 | 496 | 739
R014 | P3 | M06 | 1509 | 515 | 319
R015 | P4 | M04 | 3025 | 581 | 1998
R016 | P4 | M11 | 2962 | 815 | 1206
R017 | P4 | M07 | 5731 | 1811 | 1217
R018 | P4 | M14 | 11522 | 2188 | 6248
R019 | P4 | M13 | 10922 | 3675 | 2661
R020 | P4 | M12 | 9924 | 2137 | 3687
R021 | P5 | M09 | 9805 | 3039 | 2275
R022 | P5 | M07 | 10058 | 1839 | 4836
R023 | P5 | M05 | 5227 | 789 | 1344
R024 | P5 | M08 | 11204 | 3744 | 4812
R025 | P5 | M01 | 5980 | 1126 | 2144
R026 | P5 | M04 | 2289 | 473 | 471
R027 | P6 | M01 | 10434 | 2021 | 4873
R028 | P6 | M07 | 2737 | 897 | 680
R029 | P6 | M11 | 1949 | 559 | 782
R030 | P6 | M13 | 7554 | 1860 | 4929
R031 | P6 | M09 | 5814 | 1252 | 3386
R032 | P6 | M03 | 5191 | 1163 | 1971
R033 | P6 | M04 | 10570 | 3572 | 6917
R034 | P7 | M06 | 9300 | 2739 | 3747
R035 | P7 | M09 | 3937 | 910 | 1213
R036 | P7 | M12 | 11771 | 3214 | 2489
R037 | P7 | M14 | 10915 | 2746 | 5185
R038 | P7 | M07 | 11371 | 2904 | 4666
R039 | P8 | M01 | 5201 | 835 | 2820
R040 | P8 | M14 | 3303 | 1115 | 1525
R041 | P8 | M04 | 4602 | 1025 | 1276
R042 | P8 | M10 | 9874 | 2054 | 2651
R043 | P8 | M13 | 8378 | 2248 | 4042
R044 | P8 | M03 | 609 | 95 | 201

## Purchase_Orders
Purchase_Orders
Commitments to a supplier for a project (order & expected-delivery dates).
po_id | supplier_id | project_id | order_date | expected_delivery | status
PO0001 | SUP-D | P1 | 2026-06-27 | 2026-07-02 | Received
PO0002 | SUP-D | P1 | 2026-03-23 | 2026-03-28 | Received
PO0003 | SUP-B | P1 | 2026-05-16 | 2026-05-28 | Received
PO0004 | SUP-D | P1 | 2026-03-15 | 2026-03-20 | Received
PO0005 | SUP-F | P1 | 2026-06-09 | 2026-06-19 | Received
PO0006 | SUP-F | P2 | 2026-05-20 | 2026-05-30 | Received
PO0007 | SUP-D | P2 | 2026-05-20 | 2026-05-25 | Received
PO0008 | SUP-D | P2 | 2026-04-09 | 2026-04-14 | Received
PO0009 | SUP-H | P2 | 2026-05-11 | 2026-05-16 | Received
PO0010 | SUP-H | P2 | 2026-04-05 | 2026-04-10 | Received
PO0011 | SUP-E | P2 | 2026-03-10 | 2026-03-14 | Received
PO0012 | SUP-E | P2 | 2026-06-25 | 2026-06-29 | Received
PO0013 | SUP-C | P3 | 2026-06-08 | 2026-06-23 | Received
PO0014 | SUP-D | P3 | 2026-06-09 | 2026-06-14 | Received
PO0015 | SUP-F | P3 | 2026-03-14 | 2026-03-24 | Received
PO0016 | SUP-F | P3 | 2026-03-08 | 2026-03-18 | Received
PO0017 | SUP-G | P3 | 2026-03-18 | 2026-03-25 | Received
PO0018 | SUP-G | P3 | 2026-03-11 | 2026-03-18 | Received
PO0019 | SUP-G | P3 | 2026-05-31 | 2026-06-07 | Received
PO0020 | SUP-D | P4 | 2026-06-27 | 2026-07-02 | Received
PO0021 | SUP-F | P4 | 2026-03-20 | 2026-03-30 | Received
PO0022 | SUP-F | P4 | 2026-05-03 | 2026-05-13 | Received
PO0023 | SUP-D | P4 | 2026-06-14 | 2026-06-19 | Received
PO0024 | SUP-D | P4 | 2026-07-11 | 2026-07-16 | Received
PO0025 | SUP-D | P4 | 2026-03-07 | 2026-03-12 | Received
PO0026 | SUP-G | P4 | 2026-05-24 | 2026-05-31 | Received
PO0027 | SUP-D | P4 | 2026-06-12 | 2026-06-17 | Received
PO0028 | SUP-D | P4 | 2026-04-22 | 2026-04-27 | Received
PO0029 | SUP-D | P5 | 2026-06-08 | 2026-06-13 | Received
PO0030 | SUP-D | P5 | 2026-03-09 | 2026-03-14 | Received
PO0031 | SUP-E | P5 | 2026-05-21 | 2026-05-25 | Received
PO0032 | SUP-G | P5 | 2026-03-03 | 2026-03-10 | Received
PO0033 | SUP-H | P5 | 2026-03-09 | 2026-03-14 | Received
PO0034 | SUP-C | P5 | 2026-07-08 | 2026-07-23 | Open
PO0035 | SUP-D | P5 | 2026-06-17 | 2026-06-22 | Received
PO0036 | SUP-C | P6 | 2026-06-09 | 2026-06-24 | Received
PO0037 | SUP-C | P6 | 2026-04-24 | 2026-05-09 | Received
PO0038 | SUP-C | P6 | 2026-04-05 | 2026-04-20 | Received
PO0039 | SUP-F | P6 | 2026-04-13 | 2026-04-23 | Received
PO0040 | SUP-F | P6 | 2026-05-26 | 2026-06-05 | Received
PO0041 | SUP-D | P6 | 2026-05-30 | 2026-06-04 | Received
PO0042 | SUP-D | P6 | 2026-03-25 | 2026-03-30 | Received
PO0043 | SUP-D | P6 | 2026-03-04 | 2026-03-09 | Received
PO0044 | SUP-D | P6 | 2026-05-08 | 2026-05-13 | Received
PO0045 | SUP-G | P7 | 2026-03-15 | 2026-03-22 | Received
PO0046 | SUP-D | P7 | 2026-03-04 | 2026-03-09 | Received
PO0047 | SUP-D | P7 | 2026-03-06 | 2026-03-11 | Received
PO0048 | SUP-D | P7 | 2026-06-24 | 2026-06-29 | Received
PO0049 | SUP-D | P7 | 2026-04-06 | 2026-04-11 | Received
PO0050 | SUP-E | P7 | 2026-03-12 | 2026-03-16 | Received
PO0051 | SUP-C | P8 | 2026-04-23 | 2026-05-08 | Received
PO0052 | SUP-D | P8 | 2026-06-14 | 2026-06-19 | Received
PO0053 | SUP-D | P8 | 2026-05-07 | 2026-05-12 | Received
PO0054 | SUP-E | P8 | 2026-03-07 | 2026-03-11 | Received
PO0055 | SUP-E | P8 | 2026-05-11 | 2026-05-15 | Received
PO0056 | SUP-A | P8 | 2026-05-03 | 2026-05-16 | Received
PO0057 | SUP-A | P8 | 2026-04-09 | 2026-04-22 | Received

## PO_Lines
PO_Lines
The materials, quantities and unit prices on each PO.
line_id | po_id | material_id | qty_ordered | unit_price
PO0001-L1 | PO0001 | M09 | 429 | 42.16
PO0002-L1 | PO0002 | M09 | 429 | 413.88
PO0003-L1 | PO0003 | M13 | 1366 | 359.26
PO0004-L1 | PO0004 | M12 | 2415 | 263.14
PO0005-L1 | PO0005 | M11 | 8909 | 172.85
PO0006-L1 | PO0006 | M11 | 1535 | 0.83
PO0007-L1 | PO0007 | M09 | 381 | 309.36
PO0008-L1 | PO0008 | M04 | 2516 | 435.69
PO0009-L1 | PO0009 | M08 | 1077 | 507.91
PO0010-L1 | PO0010 | M08 | 1077 | 617.59
PO0011-L1 | PO0011 | M13 | 4354 | 205.76
PO0012-L1 | PO0012 | M13 | 4354 | 196.51
PO0013-L1 | PO0013 | M01 | 6835 | 413.12
PO0014-L1 | PO0014 | M14 | 831 | 699.55
PO0015-L1 | PO0015 | M03 | 3858 | 630.63
PO0016-L1 | PO0016 | M03 | 3858 | 401.18
PO0017-L1 | PO0017 | M05 | 1332 | 308.65
PO0018-L1 | PO0018 | M06 | 602 | 179.45
PO0019-L1 | PO0019 | M06 | 602 | 527.76
PO0020-L1 | PO0020 | M04 | 2414 | 665.03
PO0021-L1 | PO0021 | M11 | 1338 | 224.58
PO0022-L1 | PO0022 | M11 | 1338 | 399.62
PO0023-L1 | PO0023 | M07 | 5545 | 312.81
PO0024-L1 | PO0024 | M14 | 3766 | 528.66
PO0025-L1 | PO0025 | M14 | 3766 | 430.31
PO0026-L1 | PO0026 | M13 | 6312 | 438.07
PO0027-L1 | PO0027 | M12 | 2776 | 149.7
PO0028-L1 | PO0028 | M12 | 2776 | 183.69
PO0029-L1 | PO0029 | M09 | 4020 | 329.66
PO0030-L1 | PO0030 | M09 | 4020 | 405.48
PO0031-L1 | PO0031 | M07 | 6910 | 213.47
PO0032-L1 | PO0032 | M05 | 2701 | 642.19
PO0033-L1 | PO0033 | M08 | 7412 | 89.31
PO0034-L1 | PO0034 | M01 | 6310 | 25.42
PO0035-L1 | PO0035 | M04 | 1480 | 350.02
PO0036-L1 | PO0036 | M01 | 5273 | 163.24
PO0037-L1 | PO0037 | M01 | 5273 | 422.39
PO0038-L1 | PO0038 | M07 | 2562 | 68.36
PO0039-L1 | PO0039 | M11 | 544 | 638.01
PO0040-L1 | PO0040 | M11 | 544 | 562.09
PO0041-L1 | PO0041 | M13 | 4613 | 588.23
PO0042-L1 | PO0042 | M09 | 4395 | 147.45
PO0043-L1 | PO0043 | M03 | 4479 | 554.75
PO0044-L1 | PO0044 | M04 | 8483 | 196.02
PO0045-L1 | PO0045 | M06 | 9099 | 71.05
PO0046-L1 | PO0046 | M09 | 3228 | 699.92
PO0047-L1 | PO0047 | M12 | 7698 | 35.79
PO0048-L1 | PO0048 | M14 | 4818 | 384.82
PO0049-L1 | PO0049 | M14 | 4818 | 330.5
PO0050-L1 | PO0050 | M07 | 8180 | 458.75
PO0051-L1 | PO0051 | M01 | 4936 | 51.92
PO0052-L1 | PO0052 | M14 | 1938 | 35.75
PO0053-L1 | PO0053 | M04 | 4145 | 447.9
PO0054-L1 | PO0054 | M10 | 6349 | 624.94
PO0055-L1 | PO0055 | M13 | 7976 | 351.75
PO0056-L1 | PO0056 | M03 | 171 | 51.21
PO0057-L1 | PO0057 | M03 | 171 | 339.06

## Deliveries_GRN
Deliveries_GRN
Goods receipts against POs. qty_rejected = defective. Drives stock & supplier perf.
delivery_id | po_id | material_id | project_id | qty_received | qty_rejected | order_date | expected_date | received_date
D0001 | PO0001 | M09 | P1 | 429 | 0 | 2026-06-27 | 2026-07-02 | 2026-07-02
D0002 | PO0002 | M09 | P1 | 429 | 0 | 2026-03-23 | 2026-03-28 | 2026-03-28
D0003 | PO0003 | M13 | P1 | 1366 | 0 | 2026-05-16 | 2026-05-28 | 2026-05-28
D0004 | PO0004 | M12 | P1 | 2415 | 0 | 2026-03-15 | 2026-03-20 | 2026-03-20
D0005 | PO0005 | M11 | P1 | 8909 | 0 | 2026-06-09 | 2026-06-19 | 2026-06-19
D0006 | PO0006 | M11 | P2 | 1535 | 70 | 2026-05-20 | 2026-05-30 | 2026-05-30
D0007 | PO0007 | M09 | P2 | 381 | 0 | 2026-05-20 | 2026-05-25 | 2026-05-25
D0008 | PO0008 | M04 | P2 | 2516 | 0 | 2026-04-09 | 2026-04-14 | 2026-04-14
D0009 | PO0009 | M08 | P2 | 1077 | 0 | 2026-05-11 | 2026-05-16 | 2026-05-16
D0010 | PO0010 | M08 | P2 | 1077 | 0 | 2026-04-05 | 2026-04-10 | 2026-04-10
D0011 | PO0011 | M13 | P2 | 4354 | 0 | 2026-03-10 | 2026-03-14 | 2026-03-14
D0012 | PO0012 | M13 | P2 | 4354 | 0 | 2026-06-25 | 2026-06-29 | 2026-07-04
D0013 | PO0013 | M01 | P3 | 6835 | 0 | 2026-06-08 | 2026-06-23 | 2026-06-23
D0014 | PO0014 | M14 | P3 | 831 | 0 | 2026-06-09 | 2026-06-14 | 2026-06-14
D0015 | PO0015 | M03 | P3 | 3858 | 0 | 2026-03-14 | 2026-03-24 | 2026-03-24
D0016 | PO0016 | M03 | P3 | 3858 | 0 | 2026-03-08 | 2026-03-18 | 2026-03-18
D0017 | PO0017 | M05 | P3 | 1332 | 0 | 2026-03-18 | 2026-03-25 | 2026-03-28
D0018 | PO0018 | M06 | P3 | 602 | 0 | 2026-03-11 | 2026-03-18 | 2026-03-18
D0019 | PO0019 | M06 | P3 | 602 | 24 | 2026-05-31 | 2026-06-07 | 2026-06-07
D0020 | PO0020 | M04 | P4 | 2414 | 0 | 2026-06-27 | 2026-07-02 | 2026-07-02
D0021 | PO0021 | M11 | P4 | 1338 | 0 | 2026-03-20 | 2026-03-30 | 2026-03-30
D0022 | PO0022 | M11 | P4 | 1338 | 0 | 2026-05-03 | 2026-05-13 | 2026-05-13
D0023 | PO0023 | M07 | P4 | 5545 | 0 | 2026-06-14 | 2026-06-19 | 2026-06-19
D0024 | PO0024 | M14 | P4 | 3766 | 0 | 2026-07-11 | 2026-07-16 | 2026-07-16
D0025 | PO0025 | M14 | P4 | 3766 | 0 | 2026-03-07 | 2026-03-12 | 2026-03-12
D0026 | PO0026 | M13 | P4 | 6312 | 0 | 2026-05-24 | 2026-05-31 | 2026-06-08
D0027 | PO0027 | M12 | P4 | 2776 | 117 | 2026-06-12 | 2026-06-17 | 2026-06-20
D0028 | PO0028 | M12 | P4 | 2776 | 0 | 2026-04-22 | 2026-04-27 | 2026-04-27
D0029 | PO0029 | M09 | P5 | 4020 | 0 | 2026-06-08 | 2026-06-13 | 2026-06-26
D0030 | PO0030 | M09 | P5 | 4020 | 0 | 2026-03-09 | 2026-03-14 | 2026-03-14
D0031 | PO0031 | M07 | P5 | 6910 | 0 | 2026-05-21 | 2026-05-25 | 2026-05-25
D0032 | PO0032 | M05 | P5 | 2701 | 47 | 2026-03-03 | 2026-03-10 | 2026-03-10
D0033 | PO0033 | M08 | P5 | 7412 | 0 | 2026-03-09 | 2026-03-14 | 2026-03-14
D0034 | PO0035 | M04 | P5 | 1480 | 70 | 2026-06-17 | 2026-06-22 | 2026-06-22
D0035 | PO0036 | M01 | P6 | 5273 | 0 | 2026-06-09 | 2026-06-24 | 2026-06-24
D0036 | PO0037 | M01 | P6 | 5273 | 0 | 2026-04-24 | 2026-05-09 | 2026-05-09
D0037 | PO0038 | M07 | P6 | 2562 | 0 | 2026-04-05 | 2026-04-20 | 2026-04-20
D0038 | PO0039 | M11 | P6 | 544 | 0 | 2026-04-13 | 2026-04-23 | 2026-04-26
D0039 | PO0040 | M11 | P6 | 544 | 0 | 2026-05-26 | 2026-06-05 | 2026-06-05
D0040 | PO0041 | M13 | P6 | 4613 | 0 | 2026-05-30 | 2026-06-04 | 2026-06-16
D0041 | PO0042 | M09 | P6 | 4395 | 0 | 2026-03-25 | 2026-03-30 | 2026-03-30
D0042 | PO0043 | M03 | P6 | 4479 | 0 | 2026-03-04 | 2026-03-09 | 2026-03-09
D0043 | PO0044 | M04 | P6 | 8483 | 0 | 2026-05-08 | 2026-05-13 | 2026-05-13
D0044 | PO0045 | M06 | P7 | 9099 | 118 | 2026-03-15 | 2026-03-22 | 2026-04-03
D0045 | PO0046 | M09 | P7 | 3228 | 0 | 2026-03-04 | 2026-03-09 | 2026-03-09
D0046 | PO0047 | M12 | P7 | 7698 | 0 | 2026-03-06 | 2026-03-11 | 2026-03-11
D0047 | PO0048 | M14 | P7 | 4818 | 160 | 2026-06-24 | 2026-06-29 | 2026-06-29
D0048 | PO0049 | M14 | P7 | 4818 | 0 | 2026-04-06 | 2026-04-11 | 2026-04-11
D0049 | PO0050 | M07 | P7 | 8180 | 0 | 2026-03-12 | 2026-03-16 | 2026-03-16
D0050 | PO0051 | M01 | P8 | 4936 | 0 | 2026-04-23 | 2026-05-08 | 2026-05-08
D0051 | PO0052 | M14 | P8 | 1938 | 0 | 2026-06-14 | 2026-06-19 | 2026-06-19
D0052 | PO0053 | M04 | P8 | 4145 | 0 | 2026-05-07 | 2026-05-12 | 2026-05-12
D0053 | PO0054 | M10 | P8 | 6349 | 0 | 2026-03-07 | 2026-03-11 | 2026-03-11
D0054 | PO0055 | M13 | P8 | 7976 | 0 | 2026-05-11 | 2026-05-15 | 2026-05-15
D0055 | PO0056 | M03 | P8 | 171 | 0 | 2026-05-03 | 2026-05-16 | 2026-05-16
D0056 | PO0057 | M03 | P8 | 171 | 0 | 2026-04-09 | 2026-04-22 | 2026-04-22

## Invoices
Invoices
Supplier invoices → 3-way matched against the PO and the delivery.
invoice_id | po_id | supplier_id | invoice_date | billed_qty | amount
INV0001 | PO0001 | SUP-D | 2026-07-02 | 429 | 18087
INV0002 | PO0002 | SUP-D | 2026-03-28 | 480 | 198662
INV0003 | PO0003 | SUP-B | 2026-05-28 | 1530 | 549668
INV0004 | PO0004 | SUP-D | 2026-03-20 | 2415 | 635483
INV0005 | PO0009 | SUP-H | 2026-05-16 | 1077 | 547019
INV0006 | PO0010 | SUP-H | 2026-04-10 | 1206 | 744814
INV0007 | PO0011 | SUP-E | 2026-03-14 | 4354 | 895879
INV0008 | PO0012 | SUP-E | 2026-07-04 | 4354 | 855605
INV0009 | PO0013 | SUP-C | 2026-06-23 | 6835 | 2823675
INV0010 | PO0016 | SUP-F | 2026-03-18 | 3858 | 1547752
INV0011 | PO0017 | SUP-G | 2026-03-28 | 1332 | 411122
INV0012 | PO0018 | SUP-G | 2026-03-18 | 602 | 108029
INV0013 | PO0019 | SUP-G | 2026-06-07 | 578 | 305045
INV0014 | PO0020 | SUP-D | 2026-07-02 | 2414 | 1605382
INV0015 | PO0021 | SUP-F | 2026-03-30 | 1338 | 300488
INV0016 | PO0022 | SUP-F | 2026-05-13 | 1499 | 599030
INV0017 | PO0024 | SUP-D | 2026-07-16 | 3766 | 1990934
INV0018 | PO0026 | SUP-G | 2026-06-08 | 6312 | 2765098
INV0019 | PO0028 | SUP-D | 2026-04-27 | 3109 | 571092
INV0020 | PO0029 | SUP-D | 2026-06-26 | 4020 | 1325233
INV0021 | PO0030 | SUP-D | 2026-03-14 | 4020 | 1630030
INV0022 | PO0031 | SUP-E | 2026-05-25 | 6910 | 1475078
INV0023 | PO0032 | SUP-G | 2026-03-10 | 2654 | 1704372
INV0024 | PO0039 | SUP-F | 2026-04-26 | 544 | 347077
INV0025 | PO0041 | SUP-D | 2026-06-16 | 4613 | 2713505
INV0026 | PO0042 | SUP-D | 2026-03-30 | 4395 | 648043
INV0027 | PO0044 | SUP-D | 2026-05-13 | 8483 | 1662838
INV0028 | PO0045 | SUP-G | 2026-04-03 | 8981 | 638100
INV0029 | PO0047 | SUP-D | 2026-03-11 | 7698 | 275511
INV0030 | PO0049 | SUP-D | 2026-04-11 | 5396 | 1783378
INV0031 | PO0051 | SUP-C | 2026-05-08 | 4936 | 256277
INV0032 | PO0054 | SUP-E | 2026-03-11 | 6349 | 3967744
INV0033 | PO0055 | SUP-E | 2026-05-15 | 7976 | 2805558
INV0034 | PO0056 | SUP-A | 2026-05-16 | 171 | 8757
INV0035 | PO0057 | SUP-A | 2026-04-22 | 192 | 65100